## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Priority | User Stories
1 | The player can obtain and complete quests | M | When doing an interaction a player completes and obtains the next quest | Jesse
2 | The player can win the game by completing certain quests | M | If a player has obtained and completed all the quests he wins the game | Erik
3 | The player can quit the game | M | if a player is finished with playing the game he has to have the chance to quit the game | Daniel
4 | The player can move to different locations | M | If a player completed all the quests on a certain location he should be able to move to all unlocked locations
5 | The player can see to which locations they can move | M | The player should have insight in some sort of list where he can see all locked and unlocked locations
6 | The player can fight monsters | M | When exploring all locations and doing quests the player has to encounter some sort of entities he kan have a fight with and get new items and stuff
7 | The player can recover health | M | If a player has taken damage in a fight he has to have the chance to use sertain health items he can find when completing quest or kill enemies
8 | The player has an inventory to hold items | S
9 | When winning a fight, the player can obtain items | S
10 | The items obtained from winning a fight are random | S
11 | When completing a quest, the player can obtain items | S
12 | Locations have descriptions | S
13 | The player can equip weapons | S
14 | When attacking, the player and monsters do a variable amount of damage | S
15 | The player may need to meet certain conditions to move to certain locations | C
16 | Multiple of the same item in the inventory are stacked | C
17 | When losing a fight, the player will automatically go to their House and regain their health
18 | When losing a fight, the monster will take a random item (except the Adventurer's Pass) from the inventory | C
19 | When winning a fight, the player gains experience | C
20 | When reaching certain experience thresholds, the player's level increases | C
21 | When reaching a new level, the player gains more health/attack/etc | C
22 | The player can hold gold | W
23 | When winning a fight, the player can obtain gold | W

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
as a software developer, i want to implement this